## Read Me
DTCC TRANSFORMATION FUNCTIONALITY CLIENT CHECKLIST GUIDE
| Table of Contents | Description
1 | Purpose of the checklist | The checklist is designed to help clients: • Understand upcoming DTCC changes that will impact their connectivity, messaging, reporting, profiles, and workflows, • Identify required client actions (e.g., onboarding, format adoption, testing, entitlements, and profile changes), • Plan migration and testing timelines using clearly labeled PSE and Production availability dates, • Avoid service disruption by tracking required migration deadlines and decommissioning dates. • Coordinate internally across technology, operations, and compliance teams using one shared source of truth.
2 | Intended audience | This document is intended for client-facing and client implementation teams, including: • Product Management, • Project / Program Management, • Technology & Integration Teams, • Agile Development / Product Owners, and • Operations Teams supporting DTCC services The Functional Client Milestone Checklist is especially useful for teams responsible for client onboarding, connectivity, messaging formats, reporting consumption, and profile management.
3 | Tabs | All tabs present different views of the SAME underlying information to support varied client use cases. Clients are welcome to download and reorganize the content as needed for internal use.
4 | Searchable Checklist | This is the heart of the document. Clients can filter by: • Service/Product (Settlement, CNS®, ETF, UTC, SDX) • Category (Connectivity, Messaging, Reporting, Settlement Enhancements, Decommissioning) • Initiative (Modernization, 24x5, SDX Portal) • Dates or task numbers Each row represents one discrete client action/task - even if similar actions apply across multiple products. These tasks DO NOT break down milestone dates like the chronological view, but line them up by task.
5 | Chronologically Sorted | The Chronologically Sorted tab breaks down tasks into milestones [PSE, Production and Final Migration], creating steps that are sorted in chronological order.
6 | Grouped Timeline | The Grouped Timeline tab groups steps by the month/quarter/year for static viewing.
7 | What you should do first when opening this document | • Focus on Required Migration Dates FIRST ◦These indicate actions that must be completed to remain compliant or operational. ◦The Checklist is organized in the order corresponding to the Functional Change Document (FCD). However, It may be helpful to sort the "Required Migration Quarter" in ascending order to better understand what needs to be completed first. • Review Connectivity and Messaging tasks early - These often require onboarding lead time, certificates, entitlements, or format development. • Filter by their applicable services/products (i.e., Settlement only, CNS® only, ETF only) • Use PSE dates to plan testing windows - PSE availability indicates when clients can start validating changes ahead of production. • Share internally across teams - Many tasks require coordination between technology, operations, and business stakeholders.
Note: The changes outlined in this document may be subject to Regulatory review and approval, which could impact both the enhancement design and implementation timelines
Searchable Checklist Data Dictionary
Column | Column Title | Description
B | # | Task Number - A task could apply to multiple services/products.
C | FCD Mapping | References the section or identifier in the Functional Change Document (FCD) where the requirement is formally described. Used to align checklist tasks with official transformation documentation.
D | Clearing/Settlement | High‑level classification of the task, indicating the functional area impacted by the change
E | Change Type | Describes the type of client action required, such as connectivity, messaging, reporting, functional enhancements, or decommissioning.
F | Product | The DTCC service or product to which the task applies. All clearing products is in green and settlement in grey.
G | Initiative | Identifies the broader program or initiative driving the change
H | Task | A concise description of the required client action or readiness activity. Explains what clients need to do, such as onboarding, connectivity changes, format adoption, testing, or profile updates.
I | Available in PSE | Indicates when the functionality, interface, or change becomes available in the Participant Services Environment (PSE) for client testing or preparation. Values may be a specific date, quarter, or “Currently Available.”
J | Available in Production | Indicates when the functionality or change is available in the Production environment. This reflects when clients can begin using the capability in live processing.
K | Required Migration Quarter | The deadline by which clients must complete migration or adoption of the change to remain compliant or operational. Missing this date may result in service impact or decommissioning of legacy functionality.
L | Required Migration Date | Estimates on migration date within the proceeding indicated quarter - dates are subject to change. All 2026 date are available, others are that are blank are TBA (to be announced)
M | Comments + Specs | Provides additional context, clarifications, dependencies, or notes to help interpret the task and associated dates.
Note: You can filter by any column by clicking on the arrow within the title of that column, including filtering by products, Equities Clearing/Settlement, task number, and more.
Change Type
Messaging/Reporting |  | Changes that impact message formats, data content, delivery methods, or reports that clients send to or receive from DTCC. This includes adoption of new standards (e.g., ISO 20022), new or enhanced reports, changes to message fields, and updates to notification or administrative messaging.
Connectivity |  | Changes that require updates to how clients technically connect to DTCC systems. This includes onboarding to new queue managers or services, migration to supported transport protocols (e.g., Distributed MQ, sFTP), certificate and security configuration updates, network or IP changes, and entitlement setup required to establish or maintain system connectivity.
Functional Changes |  | Changes that impact business processing, workflows, or system behavior rather than message formats or connectivity. These include new or enhanced settlement and clearing functionality, profile and authorization changes, processing logic updates (e.g., recycling, reintroductions, partials), and operational behavior that clients must support or configure.
Decommisioning |  | The retirement of legacy functionality that will no longer be supported after a defined migration date. This includes shutdown of obsolete message formats, reports (e.g., Print Image reports), interfaces, or workflows, and requires clients to fully transition to the designated replacement solution to avoid service disruption.
Initiative
Modernization |  | Changes driven by DTCC’s broader technology and processing modernization efforts. This includes migration to new platforms and standards (e.g., ISO 20022), replacement of legacy formats or interfaces, enhanced settlement and clearing functionality, and long‑term improvements to scalability, resiliency, and client experience.
24x5 |  | Changes required to support extended trading and processing hours. These initiatives enable overnight and near‑continuous processing and may require clients to adopt new connectivity, message fields, profiles, or operational workflows to participate in 24x5 processing.
Modernization - SDX Portal |  | Changes associated with the launch and expansion of the Securities Data Experience (SDX) Portal. This includes client entitlements, adoption of new online CSV reports, replacement of legacy report delivery mechanisms (e.g., Print Image), and access to modernized data and reporting capabilities through the SDX user interface and supported channels.
MPID |  | Changes related to Market Participant Identifier (MPID) functionality and reporting. These initiatives enable enhanced trade capture, reporting, or data distribution tied to MPIDs, including support for introducing and executing broker‑dealer identification in applicable clearing services.

## Data Dictionary (hidden)
Dictionary
Column | Description
# | Task Number - A task could apply to multiple services/products
FCD Mapping | References the section or identifier in the Functional Change Document (FCD) where the requirement is formally described. Used to align checklist tasks with official transformation documentation.
Clearing/Settlement | High‑level classification of the task, indicating the functional area impacted by the change
Change Type | Describes the type of client action required, such as connectivity, messaging, reporting, functional enhancements, or decommissioning.
Product | The DTCC service or product to which the task applies. All clearing products is in green and settlement grey..
Initiative | Identifies the broader program or initiative driving the change
Task | A concise description of the required client action or readiness activity. Explains what clients need to do, such as onboarding, connectivity changes, format adoption, testing, or profile updates.
Available in PSE | Indicates when the functionality, interface, or change becomes available in the Participant Services Environment (PSE) for client testing or preparation. Values may be a specific date, quarter, or “Currently Available.”
Available in Production | Indicates when the functionality or change is available in the Production environment. This reflects when clients can begin using the capability in live processing.
Required Migration | The deadline by which clients must complete migration or adoption of the change to remain compliant or operational. Missing this date may result in service impact or decommissioning of legacy functionality.
* you can filter by any column by clicked on the arrow within the title of that column - this includes filtering by services/products, categories, task number, and more.

## Searchable Checklist
DTCC TRANSFORMATION FUNCTIONALITY CLIENT CHECKLIST | [6 empty] | Note: The changes outlined in this document may be subject to Regulatory review and approval, which could impact both the enhancement design and implementation timelines
# | FCD Mapping | Clearing/Settlement Services | Change Type | Product | Initiative | Task | Available in PSE | Available in Production | Required Migration Quarter | Required Migration Date | Comments + Specs
1 | 2.1 Connectivity | Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | 2026-01-21 | 2026-07-06 | Q3/2027 |  | Connectivity guide complete and available from DTCC integration
1 | 2.1 Connectivity | Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q1/2027 | Q2/2027 | Q3/2028 |  | Connectivity guide complete and available from DTCC integration
1 | 2.1 Connectivity | Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q1/2027 | Q4/2027 | Q3/2028 |  | Connectivity guide complete and available from DTCC integration
2 | 2.1 Connectivity | Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | 2026-01-21 | 2026-07-06 | Q3/2027 |  | Connectivity guide complete and available from DTCC integration
2 | 2.1 Connectivity | Equities Clearing | Connectivity | UTC | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q4/2027 | Q1/2028 | Q4/2028 |  | Connectivity guide complete and available from DTCC integration
2 | 2.1 Connectivity | Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q1/2027 | Q2/2027 | Q3/2028 |  | Connectivity guide complete and available from DTCC integration
2 | 2.1 Connectivity | Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q1/2027 | Q4/2027 | Q3/2028 |  | Connectivity guide complete and available from DTCC integration
3 | 2.1 Connectivity | Other | Connectivity | SDX Portal | Modernization - SDX Portal | New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | SDX portal app was provisioned to SACs on 2/20/26 | April 10 2026 | CNS® - Q4/2026 ETF - Q2/2027 Settlement - Q3/2027 | CNS® - November 16, 2026 ETF - TBA Settlement - TBA | Early adoption of SDX is encouraged
4 | 2.1 Connectivity | Equities Clearing | Connectivity | UTC | 24x5 | Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | 2026-01-11 | 2026-06-28 | Q2/2026 | 2026-06-28 | If interested in participating in 24x5, these are the required dates
5 | 2.1 Connectivity | Settlement Services | Connectivity | Settlement | Modernization | Request access to DTCC’s new ISO 20022 test facility - your SAC can grant access through entitlements | 2026-03-04 | N/A | Optional |  | Access granted by your Super Access Coordinator (SAC)
6 | 2.1 Connectivity | Settlement Services | Connectivity | Settlement | Modernization | ISO 20022 Test Facility accommodates Deliver Orders, Payment Orders | 2026-03-04 | N/A | Optional
7 | 2.1 Connectivity | Settlement Services | Connectivity | Settlement | Modernization | ISO 20022 Test Facility accommodates Position Movements & Pledges | 2026-04-30 | N/A | Optional
8 | 2.1 Connectivity [FUTURE ADDITION] | Settlement Services | Messaging/Reporting | Settlement | Modernization - SDX Portal | Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | September 30th, 2026 | Q4/2026 | Q3/2027 |  | Settlement report specifications available on DTCC Learning
9 | 2.2 Transactional Input/Output - Format & Channels | Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO message format | Q1/2027 | Q2/2027 | Q3/2028
10 | 2.2 Transactional Input/Output - Format & Channels | Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO 20022 message format | 2026-07-06 | 2026-11-13 | Q3/2027 |  | Adopt new ISO 20022 transaction messages in current production in advance of the modernized system release in September 2027
11 | 2.2 Transactional Input/Output - Format & Channels | Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX message format | Q1/2028 | Q4/2028 | Q4/2028
12 | 2.2 Transactional Input/Output - Format & Channels | Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | 2026-09-30 | 2026-11-13 | Q3/2027
12 | 2.3 Data Output - Format & Channels | Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q1/2027 | Q2/2027 | Q3/2028 |  | Production migration begins in Q2/2027 CNS® ISO-aligned CSV report specifications and new Product ID’s - target publication date Q2/2026
12 | 2.3 Data Output - Format & Channels | Equities Clearing | Messaging/Reporting | ETF | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q2/2027 | Q4/2027 | Q3/2028 |  | Production migration begins in Q4/2027; ETF CSV report specifications and new Product ID’s - target publication date Q2/2026
13 | 2.3 Data Output - Format & Channels | Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Q1/2028 | Q4/2028 | Q4/2028
14 | 2.3 Data Output - Format & Channels | Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | 2026-01-11 | 2026-06-28 | Q2/2026 | June 28,2026
15 | 2.3 Data Output - Format & Channels | Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | 2026-02-12 | 2026-06-28 | Q2/2026 | June 28,2026
16 | 2.3 Data Output - Format & Channels | Equities Clearing | Decommissioning | CNS® | Modernization | Decommissioning of Print Image reports | N/A | N/A | Q4/2026 | 2026-11-16 | Print Image reports decommission on November 16
17 | 2.3 Data Output - Format & Channels | Equities Clearing | Decommissioning | ETF | Modernization | Decommisioning of Print Image reports | N/A | N/A | TBA
18 | 2.3 Data Output - Format & Channels | Equities Clearing | Messaging/Reporting | CNS® | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | 2026-07-13 | 2026-11-16 | Q4/2026 | 2026-11-16
18 | 2.3 Data Output - Format & Channels | Equities Clearing | Messaging/Reporting | ETF | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Q1/2027 | Q2/2027 | Q2/2027 | 2027-06-28
19 | 2.4 Client Interface Implementation Plan | Other | Functional Change | All | Modernization | Obtain interface usage reports from DTC and NSCC | N/A | N/A | N/A | 2026-03-31 | Production reports are currently available and should be requested by March 31, 2026
20 | 3 Settlement Enhancements & Simplifications | Settlement Services | Functional Change | Settlement | Modernization | Obtain profile usage reports from DTC | N/A | N/A | N/A | 2026-03-31 | Production reports are currently available and should be requested by March 31, 2026
21 | 3.1 Partial Settlement Enhancements | Settlement Services | Functional Change | Settlement | Modernization | Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | September 30th, 2026 | Q3/2027 | Q3/2027
22 | 3.3.1 Deliverer Authorization | Settlement Services | Functional Change | Settlement | Modernization | Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | September 30th, 2026 | Q3/2027 | Q3/2027 |  | Member usage will be optional.
23 | 3.3.1 Deliverer Authorization | Settlement Services | Functional Change | Settlement | Modernization | Adopt simplified delivery authorization profiles | Target state Delivery Authorization profile changes can be configured in the current production environment. Only the ability to establish discrete delivery profiles for same day settling CNS® obligations is new functionality. | Currently Available | Q3/2027 |  | Recommend migration to target state profile by March 31,2027 to reduce implementation risks
24 | 3.3.1 Deliverer Authorization | Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject free DOs to RAD approval | September 30th, 2026 | Q3/2027 | Q3/2027
25 | 3.3.1 Deliverer Authorization | Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | September 30th, 2026 | Q3/2027 | Q3/2027
26 | 3.3.1 Deliverer Authorization | Settlement Services | Functional Change | Settlement | Modernization | Migration from NSCC CNS® level 1 exemption processing to DTC Deliver Authorization process (Also referenced in the Clearing section of this report.) | Currently Available | Currently Available | TBA |  | Recommend migrating to DTC functionality to reduce future implementation risk (migration date will, however, be later than Q3 2027)
27 | 3.3.2 Receiver Approval (RAD) | Settlement Services | Functional Change | Settlement | Modernization | Adopt simplified Receiver Authorized Delivery (RAD) profiles | Target state RAD profile changes can be configured in the current production environment. Only the ability to subject Free DOs to RAD is new functionality | Currently Available | Q3/2027 |  | Recommend migration to target state profile by March 31, 2027 to reduce implementation risks
28 | 3.4 Pend Processing (Recycle) | Settlement Services | Functional Change | Settlement | Modernization | Prepare to adopt simplified recycle profiles | All Recycle profile changes [except DOs] can be configured in the current production environment. | Currently Available | Q3/2027 |  | Recommend migration to target state profile by March 31, 2027 to reduce implementation risks
29 | 3.5 Reintroduce/Drop Processing | Settlement Services | Functional Change | Settlement | Modernization | Adopt for the mandatory reintroduction of failed (dropped) DO transactions | The ability to reintroduce failed trades exists in the current production environment | Currently Available | Q3/2027 |  | Recommend update profiles to simulate target state by March 31, 2027 to reduce implementation risks
30 | 4.1 UTC MIPD Reporting Enhancements | Equities Clearing | Functional Change | UTC | MPID | Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | 2026-04-30 | 2026-06-12 | Optional Change
31 | 4.5 CNS Level 1 & 2 Exemptions + 3.3.1 Deliver Authorization | Equities Clearing | Functional Change | CNS® | Modernization | Migration from NSCC level 1 exemption processing to DTC Deliver Authorization process | Currently Available | Currently Available | TBA |  | Also referenced in the Settlement section of this report
32 | N/A | Equities Clearing | Functional Change | CNS® | Modernization | Conduct regression testing of MROs including input messaging | 2026-07-13 | 2026-11-16 | N/A | N/A | Regression testing should be completed by October 9, 2026
32 | N/A | Equities Clearing | Functional Change | ETF | Modernization | Conduct regression testing of MROs including input messaging | 2026-11-23 | 2027-06-28 | N/A | N/A | Regression testing should be completed by May 28, 2027
*Recommend starting with Read-Me tab to best evaluate checklist
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. and @Kaufman, Hannah - this line item refers to RAD and should probably be adjusted in the FCD and then categorized on the checklist under RAD section

## Chronologically Sorted
DTCC TRANSFORMATION FUNCTIONALITY CLIENT CHECKLIST - CHRONOLOGICALLY SORTED | [5 empty] | Note: The changes outlined in this document may be subject to Regulatory review and approval, which could impact both the enhancement design and implementation timelines
Clearing/Settlement Services | Change Type | Product | Initiative | Task | Milestone | Date | Year | Quarter | SortedDate | Comments + Specs | FCD Mapping
Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | Available in PSE | 2026-01-11 | 2026 | Q1 | 2026-01-11 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | UTC | 24x5 | Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | Available in PSE | 2026-01-11 | 2026 | Q1 | 2026-01-11 | If interested in participating in 24x5, these are the required dates | 2.1 Connectivity
Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Available in PSE | 2026-01-21 | 2026 | Q1 | 2026-01-21 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in PSE | 2026-01-21 | 2026 | Q1 | 2026-01-21 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | Available in PSE | 2026-02-12 | 2026 | Q1 | 2026-02-12 |  | 2.3 Data Output - Format & Channels
Settlement Services | Connectivity | Settlement | Modernization | ISO 20022 Test Facility accommodates Deliver Orders, Payment Orders | Available in PSE | 2026-03-04 | 2026 | Q1 | 2026-03-04 |  | 2.1 Connectivity
Settlement Services | Connectivity | Settlement | Modernization | Request access to DTCC’s new ISO 20022 test facility - your SAC can grant access through entitlements | Available in PSE | 2026-03-04 | 2026 | Q1 | 2026-03-04 | Access granted by your Super Access Coordinator (SAC) | 2.1 Connectivity
Other | Connectivity | SDX Portal | Modernization - SDX Portal | New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | Available in Production | End-March 2026 | 2026 | Q1 | 2026-03-31 | Early adoption of SDX is encouraged | 2.1 Connectivity
Other | Functional Change | All | Modernization | Obtain interface usage reports from DTC and NSCC | Required Migration | 2026-03-31 | N/A | N/A |  | Production reports are currently available and should be requested by March 31, 2026 | 2.4 Client Interface Implementation Plan
Settlement Services | Functional Change | Settlement | Modernization | Obtain profile usage reports from DTC | Required Migration | 2026-03-31 | N/A | N/A |  | Production reports are currently available and should be requested by March 31, 2026 | 3 Settlement Enhancements & Simplifications
Equities Clearing | Functional Change | UTC | MPID | Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | Available in PSE | 2026-04-30 | 2026 | Q2 | 2026-04-30 |  | 4.1 UTC MIPD Reporting Enhancements
Settlement Services | Connectivity | Settlement | Modernization | ISO 20022 Test Facility accommodates Position Movements & Pledges | Available in PSE | 2026-04-30 | 2026 | Q2 | 2026-04-30 |  | 2.1 Connectivity
Equities Clearing | Functional Change | UTC | MPID | Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | Available in Production | 2026-06-12 | 2026 | Q2 | 2026-06-12 |  | 4.1 UTC MIPD Reporting Enhancements
Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | Available in Production | 2026-06-28 | 2026 | Q2 | 2026-06-28 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | UTC | 24x5 | Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | Required Migration | 2026-06-28 | 2026 | Q2 | 2026-06-28 | If interested in participating in 24x5, these are the required dates | 2.1 Connectivity
Equities Clearing | Connectivity | UTC | 24x5 | Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | Available in Production | 2026-06-28 | 2026 | Q2 | 2026-06-28 | If interested in participating in 24x5, these are the required dates | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | Available in Production | 2026-06-28 | 2026 | Q2 | 2026-06-28 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | Required Migration | June 28,2026 | 2026 | Q2 | 2026-06-28 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Messaging/Reporting | UTC | 24x5 | Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | Required Migration | June 28,2026 | 2026 | Q2 | 2026-06-28 |  | 2.3 Data Output - Format & Channels
Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Available in Production | 2026-07-06 | 2026 | Q3 | 2026-07-06 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO 20022 message format | Available in PSE | 2026-07-06 | 2026 | Q3 | 2026-07-06 | Adopt new ISO 20022 transaction messages in current production in advance of the modernized system release in September 2027 | 2.2 Transactional Input/Output - Format & Channels
Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in Production | 2026-07-06 | 2026 | Q3 | 2026-07-06 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Functional Change | CNS® | Modernization | Conduct regression testing of MROs including input messaging | Available in PSE | 2026-07-13 | 2026 | Q3 | 2026-07-13 | Regression testing should be completed by October 9, 2026 | N/A
Equities Clearing | Messaging/Reporting | CNS® | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Available in PSE | 2026-07-13 | 2026 | Q3 | 2026-07-13 |  | 2.3 Data Output - Format & Channels
Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Available in PSE | 2026-09-30 | 2026 | Q3 | 2026-09-30 |  | 2.2 Transactional Input/Output - Format & Channels
Settlement Services | Messaging/Reporting | Settlement | Modernization - SDX Portal | Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | Available in PSE | September 30th, 2026 | 2026 | Q3 | 2026-09-30 | Settlement report specifications available on DTCC Learning | 2.1 Connectivity [FUTURE ADDITION]
Settlement Services | Functional Change | Settlement | Modernization | Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | Available in PSE | September 30th, 2026 | 2026 | Q3 | 2026-09-30 |  | 3.1 Partial Settlement Enhancements
Settlement Services | Functional Change | Settlement | Modernization | Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | Available in PSE | September 30th, 2026 | 2026 | Q3 | 2026-09-30 | Member usage will be optional. | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject free DOs to RAD approval | Available in PSE | September 30th, 2026 | 2026 | Q3 | 2026-09-30 |  | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | Available in PSE | September 30th, 2026 | 2026 | Q3 | 2026-09-30 |  | 3.3.1 Deliverer Authorization
Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Available in Production | 2026-11-13 | 2026 | Q4 | 2026-11-13 |  | 2.2 Transactional Input/Output - Format & Channels
Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO 20022 message format | Available in Production | 2026-11-13 | 2026 | Q4 | 2026-11-13 | Adopt new ISO 20022 transaction messages in current production in advance of the modernized system release in September 2027 | 2.2 Transactional Input/Output - Format & Channels
Equities Clearing | Decommissioning | CNS® | Modernization | Decommissioning of Print Image reports | Required Migration | 2026-11-16 | 2026 | Q4 | 2026-11-16 | Print Image reports decommission on November 16 | 2.3 Data Output - Format & Channels
Equities Clearing | Functional Change | CNS® | Modernization | Conduct regression testing of MROs including input messaging | Available in Production | 2026-11-16 | 2026 | Q4 | 2026-11-16 | Regression testing should be completed by October 9, 2026 | N/A
Equities Clearing | Messaging/Reporting | CNS® | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Available in Production | 2026-11-16 | 2026 | Q4 | 2026-11-16 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Messaging/Reporting | CNS® | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Required Migration | 2026-11-16 | 2026 | Q4 | 2026-11-16 |  | 2.3 Data Output - Format & Channels
Other | Connectivity | SDX Portal | Modernization - SDX Portal | New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | Required Migration | CNS® - November 16, 2026 ETF - TBA Settlement - TBA | 2026 | Q4 | 2026-11-16 | Early adoption of SDX is encouraged | 2.1 Connectivity
Equities Clearing | Functional Change | ETF | Modernization | Conduct regression testing of MROs including input messaging | Available in PSE | 2026-11-23 | 2026 | Q4 | 2026-11-23 | Regression testing should be completed by May 28, 2027 | N/A
Settlement Services | Messaging/Reporting | Settlement | Modernization - SDX Portal | Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | Available in Production | Q4/2026 | 2026 | Q4 | 2026-12-31 | Settlement report specifications available on DTCC Learning | 2.1 Connectivity [FUTURE ADDITION]
Equities Clearing | Functional Change | ETF | Modernization | Conduct regression testing of MROs including input messaging | Required Migration | 2027-03-28 | N/A | N/A |  | Regression testing should be completed by May 28, 2027 | N/A
Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in PSE | Q1/2027 | 2027 | Q1 | 2027-03-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Available in PSE | Q1/2027 | 2027 | Q1 | 2027-03-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO message format | Available in PSE | Q1/2027 | 2027 | Q1 | 2027-03-31 |  | 2.2 Transactional Input/Output - Format & Channels
Equities Clearing | Messaging/Reporting | ETF | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Available in PSE | Q1/2027 | 2027 | Q1 | 2027-03-31 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Available in PSE | Q1/2027 | 2027 | Q1 | 2027-03-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Available in PSE | Q1/2027 | 2027 | Q1 | 2027-03-31 | Production migration begins in Q2/2027 CNS® ISO-aligned CSV report specifications and new Product ID’s - target publication date Q2/2026 | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in PSE | Q1/2027 | 2027 | Q1 | 2027-03-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | ETF | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Available in Production | 2027-06-28 | 2027 | Q2 | 2027-06-28 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Messaging/Reporting | ETF | Modernization - SDX Portal | Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Required Migration | 2027-06-28 | 2027 | Q2 | 2027-06-28 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Functional Change | ETF | Modernization | Conduct regression testing of MROs including input messaging | Available in Production | 2027-06-28 | 2027 | Q2 | 2027-06-28 | Regression testing should be completed by May 28, 2027 | N/A
Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO message format | Available in Production | Q2/2027 | 2027 | Q2 | 2027-06-30 |  | 2.2 Transactional Input/Output - Format & Channels
Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Available in Production | Q2/2027 | 2027 | Q2 | 2027-06-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Available in Production | Q2/2027 | 2027 | Q2 | 2027-06-30 | Production migration begins in Q2/2027 CNS® ISO-aligned CSV report specifications and new Product ID’s - target publication date Q2/2026 | 2.3 Data Output - Format & Channels
Equities Clearing | Messaging/Reporting | ETF | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Available in PSE | Q2/2027 | 2027 | Q2 | 2027-06-30 | Production migration begins in Q4/2027; ETF CSV report specifications and new Product ID’s - target publication date Q2/2026 | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in Production | Q2/2027 | 2027 | Q2 | 2027-06-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Settlement Services | Functional Change | Settlement | Modernization | Prepare to adopt simplified recycle profiles | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Recommend migration to target state profile by March 31, 2027 to reduce implementation risks | 3.4 Pend Processing (Recycle)
Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject free DOs to RAD approval | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 |  | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject free DOs to RAD approval | Available in Production | Q3/2027 | 2027 | Q3 | 2027-09-30 |  | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | Available in Production | Q3/2027 | 2027 | Q3 | 2027-09-30 |  | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | Adopt for the mandatory reintroduction of failed (dropped) DO transactions | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Recommend update profiles to simulate target state by March 31, 2027 to reduce implementation risks | 3.5 Reintroduce/Drop Processing
Settlement Services | Functional Change | Settlement | Modernization | Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Member usage will be optional. | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 |  | 3.3.1 Deliverer Authorization
Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Settlement Services | Connectivity | Settlement | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Settlement Services | Functional Change | Settlement | Modernization | Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | Available in Production | Q3/2027 | 2027 | Q3 | 2027-09-30 | Member usage will be optional. | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | Available in Production | Q3/2027 | 2027 | Q3 | 2027-09-30 |  | 3.1 Partial Settlement Enhancements
Settlement Services | Functional Change | Settlement | Modernization | Adopt simplified Receiver Authorized Delivery (RAD) profiles | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Recommend migration to target state profile by March 31, 2027 to reduce implementation risks | 3.3.2 Receiver Approval (RAD)
Settlement Services | Messaging/Reporting | Settlement | Modernization - SDX Portal | Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Settlement report specifications available on DTCC Learning | 2.1 Connectivity [FUTURE ADDITION]
Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO 20022 message format | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Adopt new ISO 20022 transaction messages in current production in advance of the modernized system release in September 2027 | 2.2 Transactional Input/Output - Format & Channels
Settlement Services | Functional Change | Settlement | Modernization | Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 |  | 3.1 Partial Settlement Enhancements
Settlement Services | Messaging/Reporting | Settlement | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 |  | 2.2 Transactional Input/Output - Format & Channels
Settlement Services | Functional Change | Settlement | Modernization | Adopt simplified delivery authorization profiles | Required Migration | Q3/2027 | 2027 | Q3 | 2027-09-30 | Recommend migration to target state profile by March 31,2027 to reduce implementation risks | 3.3.1 Deliverer Authorization
Equities Clearing | Connectivity | UTC | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in PSE | Q4/2027 | 2027 | Q4 | 2027-12-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in Production | Q4/2027 | 2027 | Q4 | 2027-12-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | ETF | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Available in Production | Q4/2027 | 2027 | Q4 | 2027-12-31 | Production migration begins in Q4/2027; ETF CSV report specifications and new Product ID’s - target publication date Q2/2026 | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Available in Production | Q4/2027 | 2027 | Q4 | 2027-12-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX message format | Available in PSE | Q1/2028 | 2028 | Q1 | 2028-03-31 |  | 2.2 Transactional Input/Output - Format & Channels
Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Available in PSE | Q1/2028 | 2028 | Q1 | 2028-03-31 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | UTC | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Available in Production | Q1/2028 | 2028 | Q1 | 2028-03-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Required Migration | Q3/2028 | 2028 | Q3 | 2028-09-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | ETF | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Required Migration | Q3/2028 | 2028 | Q3 | 2028-09-30 | Production migration begins in Q4/2027; ETF CSV report specifications and new Product ID’s - target publication date Q2/2026 | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Required Migration | Q3/2028 | 2028 | Q3 | 2028-09-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Required Migration | Q3/2028 | 2028 | Q3 | 2028-09-30 | Production migration begins in Q2/2027 CNS® ISO-aligned CSV report specifications and new Product ID’s - target publication date Q2/2026 | 2.3 Data Output - Format & Channels
Equities Clearing | Connectivity | ETF | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Required Migration | Q3/2028 | 2028 | Q3 | 2028-09-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | CNS® | Modernization | Adopt new ISO message format | Required Migration | Q3/2028 | 2028 | Q3 | 2028-09-30 |  | 2.2 Transactional Input/Output - Format & Channels
Equities Clearing | Connectivity | CNS® | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Required Migration | Q3/2028 | 2028 | Q3 | 2028-09-30 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Connectivity | UTC | Modernization | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Required Migration | Q4/2028 | 2028 | Q4 | 2028-12-31 | Connectivity guide complete and available from DTCC integration | 2.1 Connectivity
Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Available in Production | Q4/2028 | 2028 | Q4 | 2028-12-31 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Required Migration | Q4/2028 | 2028 | Q4 | 2028-12-31 |  | 2.3 Data Output - Format & Channels
Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX message format | Required Migration | Q4/2028 | 2028 | Q4 | 2028-12-31 |  | 2.2 Transactional Input/Output - Format & Channels
Equities Clearing | Messaging/Reporting | UTC | Modernization | Adopt new FIX message format | Available in Production | Q4/2028 | 2028 | Q4 | 2028-12-31 |  | 2.2 Transactional Input/Output - Format & Channels
Settlement Services | Functional Change | Settlement | Modernization | Prepare to adopt simplified recycle profiles | Available in PSE | All Recycle profile changes [except DOs] can be configured in the current production environment. | N/A | N/A |  | Recommend migration to target state profile by March 31, 2027 to reduce implementation risks | 3.4 Pend Processing (Recycle)
Settlement Services | Connectivity | Settlement | Modernization | Request access to DTCC’s new ISO 20022 test facility - your SAC can grant access through entitlements | Required Migration | Optional | N/A | N/A |  | Access granted by your Super Access Coordinator (SAC) | 2.1 Connectivity
Settlement Services | Connectivity | Settlement | Modernization | ISO 20022 Test Facility accommodates Deliver Orders, Payment Orders | Required Migration | Optional | N/A | N/A |  |  | 2.1 Connectivity
Settlement Services | Connectivity | Settlement | Modernization | ISO 20022 Test Facility accommodates Position Movements & Pledges | Required Migration | Optional | N/A | N/A |  |  | 2.1 Connectivity
Equities Clearing | Functional Change | UTC | MPID | Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | Required Migration | Optional Change | N/A | N/A |  |  | 4.1 UTC MIPD Reporting Enhancements
Other | Connectivity | SDX Portal | Modernization - SDX Portal | New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | Available in PSE | SDX portal app was provisioned to SACs on 2/20/26 | N/A | N/A |  | Early adoption of SDX is encouraged | 2.1 Connectivity
Equities Clearing | Decommissioning | ETF | Modernization | Decommisioning of Print Image reports | Required Migration | TBA | N/A | N/A |  |  | 2.3 Data Output - Format & Channels
Equities Clearing | Functional Change | CNS® | Modernization | Migration from NSCC level 1 exemption processing to DTC Deliver Authorization process | Required Migration | TBA | N/A | N/A |  | Also referenced in the Settlement section of this report | 4.5 CNS Level 1 & 2 Exemptions + 3.3.1 Deliver Authorization
Settlement Services | Functional Change | Settlement | Modernization | Migration from NSCC CNS® level 1 exemption processing to DTC Deliver Authorization process (Also referenced in the Clearing section of this report.) | Required Migration | TBA | N/A | N/A |  | Recommend migrating to DTC functionality to reduce future implementation risk (migration date will, however, be later than Q3 2027) | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | Adopt simplified delivery authorization profiles | Available in PSE | Target state Delivery Authorization profile changes can be configured in the current production environment. Only the ability to establish discrete delivery profiles for same day settling CNS® obligations is new functionality. | N/A | N/A |  | Recommend migration to target state profile by March 31,2027 to reduce implementation risks | 3.3.1 Deliverer Authorization
Settlement Services | Functional Change | Settlement | Modernization | Adopt simplified Receiver Authorized Delivery (RAD) profiles | Available in PSE | Target state RAD profile changes can be configured in the current production environment. Only the ability to subject Free DOs to RAD is new functionality | N/A | N/A |  | Recommend migration to target state profile by March 31, 2027 to reduce implementation risks | 3.3.2 Receiver Approval (RAD)
Settlement Services | Functional Change | Settlement | Modernization | Adopt for the mandatory reintroduction of failed (dropped) DO transactions | Available in PSE | The ability to reintroduce failed trades exists in the current production environment | N/A | N/A |  | Recommend update profiles to simulate target state by March 31, 2027 to reduce implementation risks | 3.5 Reintroduce/Drop Processing

## Grouped Timeline
DTCC TRANSFORMATION FUNCTIONALITY CLIENT CHECKLIST - MILESTONE TIMELINE | Note: The changes outlined in this document may be subject to Regulatory review and approval, which could impact both the enhancement design and implementation timelines.
Quarters are shown when specific dates are not yet available.
Tasks | Predicted Date
2026
Q1
Jan
Available in PSE
Connectivity
Settlement
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | 21-Jan-26
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | 21-Jan-26
UTC
Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | 11-Jan-26
Messaging/Reporting
UTC
Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | 11-Jan-26
Feb
Available in PSE
Messaging/Reporting
UTC
Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | 12-Feb-26
Mar
Available in Production
Connectivity
SDX Portal
New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | End-March 2026
Available in PSE
Connectivity
Settlement
ISO 20022 Test Facility accommodates Deliver Orders, Payment Orders | 4-Mar-26
Request access to DTCC’s new ISO 20022 test facility - your SAC can grant access through entitlements | 4-Mar-26
Q2
Apr
Available in PSE
Connectivity
Settlement
ISO 20022 Test Facility accommodates Position Movements & Pledges | 30-Apr-26
Functional Change
UTC
Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | 30-Apr-26
Jun
Available in Production
Connectivity
UTC
Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | 28-Jun-26
Functional Change
UTC
Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | 12-Jun-26
Messaging/Reporting
UTC
Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | 28-Jun-26
Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | 28-Jun-26
Required Migration
Connectivity
UTC
Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | 28-Jun-26
Messaging/Reporting
UTC
Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | June 28,2026
Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | June 28,2026
Q3
Jul
Available in Production
Connectivity
Settlement
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | 6-Jul-26
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | 6-Jul-26
Available in PSE
Functional Change
CNS®
Conduct regression testing of MROs including input messaging | 13-Jul-26
Messaging/Reporting
CNS®
Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | 13-Jul-26
Settlement
Adopt new ISO 20022 message format | 6-Jul-26
Sep
Available in PSE
Functional Change
Settlement
Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | September 30th, 2026
New profile option - Prepare for the ability to subject free DOs to RAD approval | September 30th, 2026
New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | September 30th, 2026
Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | September 30th, 2026
Messaging/Reporting
Settlement
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | 30-Sep-26
Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | September 30th, 2026
Q4
Nov
Available in Production
Functional Change
CNS®
Conduct regression testing of MROs including input messaging | 16-Nov-26
Messaging/Reporting
CNS®
Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | 16-Nov-26
Settlement
Adopt new ISO 20022 message format | 13-Nov-26
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | 13-Nov-26
Available in PSE
Functional Change
ETF
Conduct regression testing of MROs including input messaging | 23-Nov-26
Required Migration
Connectivity
SDX Portal
New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | CNS® - November 16, 2026 ETF - TBA Settlement - TBA
Decommissioning
CNS®
Decommissioning of Print Image reports | 16-Nov-26
Messaging/Reporting
CNS®
Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | 16-Nov-26
Dec
Available in Production
Messaging/Reporting
Settlement
Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | Q4/2026
2027
Q1
Mar
Available in PSE
Connectivity
CNS®
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q1/2027
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q1/2027
ETF
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q1/2027
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q1/2027
Messaging/Reporting
CNS®
Adopt new ISO message format | Q1/2027
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q1/2027
ETF
Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | Q1/2027
Q2
Jun
Available in Production
Connectivity
CNS®
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q2/2027
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q2/2027
Functional Change
ETF
Conduct regression testing of MROs including input messaging | 28-Jun-27
Messaging/Reporting
CNS®
Adopt new ISO message format | Q2/2027
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q2/2027
ETF
Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | 28-Jun-27
Available in PSE
Messaging/Reporting
ETF
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q2/2027
Required Migration
Messaging/Reporting
ETF
Adopt/Test new online CSV reports (replacement of Print Image Format) - Available through the SDX Portal | 28-Jun-27
Q3
Sep
Available in Production
Functional Change
Settlement
Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | Q3/2027
New profile option - Prepare for the ability to subject free DOs to RAD approval | Q3/2027
New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | Q3/2027
Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | Q3/2027
Required Migration
Connectivity
Settlement
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q3/2027
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q3/2027
Functional Change
Settlement
Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | Q3/2027
Adopt for the mandatory reintroduction of failed (dropped) DO transactions | Q3/2027
Adopt simplified delivery authorization profiles | Q3/2027
Adopt simplified Receiver Authorized Delivery (RAD) profiles | Q3/2027
New profile option - Prepare for the ability to subject free DOs to RAD approval | Q3/2027
New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | Q3/2027
Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | Q3/2027
Prepare to adopt simplified recycle profiles | Q3/2027
Messaging/Reporting
Settlement
Adopt new ISO 20022 message format | Q3/2027
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q3/2027
Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | Q3/2027
Q4
Dec
Available in Production
Connectivity
ETF
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q4/2027
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q4/2027
Messaging/Reporting
ETF
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q4/2027
Available in PSE
Connectivity
UTC
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q4/2027
2028
Q1
Mar
Available in Production
Connectivity
UTC
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q1/2028
Available in PSE
Messaging/Reporting
UTC
Adopt new FIX message format | Q1/2028
Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Q1/2028
Q3
Sep
Required Migration
Connectivity
CNS®
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q3/2028
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q3/2028
ETF
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q3/2028
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q3/2028
Messaging/Reporting
CNS®
Adopt new ISO message format | Q3/2028
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q3/2028
ETF
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q3/2028
Q4
Dec
Available in Production
Messaging/Reporting
UTC
Adopt new FIX message format | Q4/2028
Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Q4/2028
Required Migration
Connectivity
UTC
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q4/2028
Messaging/Reporting
UTC
Adopt new FIX message format | Q4/2028
Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Q4/2028
N/A
Available in PSE
Connectivity
SDX Portal
New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | SDX portal app was provisioned to SACs on 2/20/26
Functional Change
Settlement
Adopt for the mandatory reintroduction of failed (dropped) DO transactions | The ability to reintroduce failed trades exists in the current production environment
Adopt simplified delivery authorization profiles | Target state Delivery Authorization profile changes can be configured in the current production environment. Only the ability to establish discrete delivery profiles for same day settling CNS® obligations is new functionality.
Adopt simplified Receiver Authorized Delivery (RAD) profiles | Target state RAD profile changes can be configured in the current production environment. Only the ability to subject Free DOs to RAD is new functionality
Prepare to adopt simplified recycle profiles | All Recycle profile changes [except DOs] can be configured in the current production environment.
Required Migration
Connectivity
Settlement
ISO 20022 Test Facility accommodates Deliver Orders, Payment Orders | Optional
ISO 20022 Test Facility accommodates Position Movements & Pledges | Optional
Request access to DTCC’s new ISO 20022 test facility - your SAC can grant access through entitlements | Optional
Decommissioning
ETF
Decommisioning of Print Image reports | TBA
Functional Change
All
Obtain interface usage reports from DTC and NSCC | 31-Mar-26
CNS®
Migration from NSCC level 1 exemption processing to DTC Deliver Authorization process | TBA
ETF
Conduct regression testing of MROs including input messaging | 28-Mar-27
Settlement
Migration from NSCC CNS® level 1 exemption processing to DTC Deliver Authorization process (Also referenced in the Clearing section of this report.) | TBA
Obtain profile usage reports from DTC | 31-Mar-26
UTC
Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | Optional Change

## Static View Checklist (hidden)
DTCC TRANSFORMATION FUNCTIONALITY CLIENT CHECKLIST [Static View] | Note: The changes outlined in this document may be subject to Regulatory review and approval, which could impact both the enhancement design and implementation timelines
Initiative | All
TASK | AVAILABLE IN PARTICIPANT SERVICES ENVIRONMENT(PSE) | PRODUCTION | REQUIRED MIGRATION2 | REQUIRED MIGRATION Q# | REQUIRED MIGRATION
Equities Clearing
Connectivity
CNS®
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q1/2027 | Q2/2027 |  | Q3/2028
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q1/2027 | Q2/2027 |  | Q3/2028
ETF
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | Q1/2027 | Q4/2027 |  | Q3/2028
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q1/2027 | Q4/2027 |  | Q3/2028
UTC
Clients who connect to UTC via FIX on an existing Sending Entity will not need any new setup on their side. Clients who choose a new Sending Entity for overnight session, will have to go through a standard onboarding process to get that new Sending Entity setup. | January 11, 2026 | June 28, 2026 | June 28, 2026 | Q2/2026 | June 28, 2026
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Q4/2027 | Q1/2028 |  | Q4/2028
Decommissioning
CNS®
Decommissioning of print Image report [Available in the SDX Portal] | N/A | November 16, 2026 | November 16, 2026 | Q4/2026 | November 16, 2026
ETF
Decommisioning of print Image report [Available in the SDX Portal] | TBA | TBA |  | TBA
Functional Change
CNS®
Conduct regression testing of MROs | July 13, 2026 | November 16, 2026 | N/A | N/A | N/A
Migration from NSCC level 1 exemption processing to DTC Deliver Authorization process | Currently Available | Currently Available |  | TBA
ETF
Conduct regression testing of MROs | November 23, 2026 | June 28, 2027 | N/A | N/A | N/A
UTC
Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID) | April 30, 2026 | June 12, 2026 |  | Optional Change
Messaging/Reporting
CNS®
Adopt new ISO message format | Q1/2027 | Q2/2027 |  | Q3/2028
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q1/2027 | Q2/2027 |  | Q3/2028
0 | July 13, 2026 | November 16, 2026 | November 16, 2026 | Q4/2026 | November 16, 2026
ETF
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Q2/2027 | Q4/2027 |  | Q3/2028
0 | Q1/2027 | June 28, 2027 | June 28, 2027 | Q2/2027 | June 28, 2027
UTC
Adopt new FIX message format | Q1/2028 | Q4/2028 |  | Q4/2028
Adopt new FIX-aligned CSV reports (replaces machine-readable output (MRO)) | Q1/2028 | Q4/2028 |  | Q4/2028
Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on input (all sending entities participating in 24x5) | February 12, 2026 | June 28, 2026 | June 28,2026 | Q2/2026 | June 28,2026
Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | January 11, 2026 | June 28, 2026 | June 28,2026 | Q2/2026 | June 28,2026
Other
Connectivity
SDX Portal
New Securities Data Experience (SDX) service is being launched - SDX Portal Application Entitlements | SDX portal app was provisioned to SACs on 2/20/26 | End-March 2026 | CNS® - November 16, 2026 ETF - TBA Settlement - TBA | CNS® - Q4/2026 ETF - Q2/2027 Settlement - Q3/2027 | CNS® - November 16, 2026 ETF - TBA Settlement - TBA
Functional Change
All
Obtain interface usage reports from DTC and NSCC | N/A | N/A |  | N/A
Settlement Services
Connectivity
Settlement
Clients who send and/or receive messages from DTCC will need to connect to the new Queue Managers (QMgrs) on the Distributed MQ service. MQ clients are required to provide the appropriate network details along with the TLS Certificate Distinguished Name (DN) information used for peer-name validation. | January 21, 2026 | July 6, 2026 |  | Q3/2027
Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | January 21, 2026 | July 6, 2026 |  | Q3/2027
ISO 20022 Test Facility accommodates Deliver Orders, Payment Orders | March 4, 2026 | N/A |  | Optional
ISO 20022 Test Facility accommodates Position Movements, Pledges, Collateral Loans | March 29, 2026 | N/A |  | Optional
Request access to DTCC’s new ISO 20022 test facility - your SAC can grant access through entitlements | March 4, 2026 | N/A |  | Optional
Decommissioning
Settlement
Decommissioning of print Image reports [Available in the SDX Portal] | September 30, 2026 | November 13, 2026 | Q3/2027 | Q3/2027 | Q3/2027
Functional Change
Settlement
Accommodate the ability to submit DO and PO transactions with a “hold” indicator. | September 30th, 2026 | Q3/2027 |  | Q3/2027
Adopt for the mandatory reintroduction of failed (dropped) DO transactions | The ability to reintroduce failed trades exists in the current production environment | Currently Available |  | Q3/2027
Adopt simplified delivery authorization profiles | Target state Delivery Authorization profile changes can be configured in the current production environment. Only the ability to establish discrete delivery profiles for same day settling CNS® obligations is new functionality. | Currently Available |  | Q3/2027
Adopt simplified Receiver Authorized Delivery (RAD) profiles | Target state RAD profile changes can be configured in the current production environment. Only the ability to subject Free DOs to RAD is new functionality | Currently Available |  | Q3/2027
Migration from NSCC CNS® level 1 exemption processing to DTC Deliver Authorization process (Also referenced in the Clearing section of this report.) | Currently Available | Currently Available |  | TBA
New profile option - Prepare for the ability to subject free DOs to RAD approval | September 30th, 2026 | Q3/2027 |  | Q3/2027
New profile option - Prepare for the ability to subject same day settling CNS® obligations to Deliverer Authorization | September 30th, 2026 | Q3/2027 |  | Q3/2027
Obtain profile usage reports from DTC | N/A | N/A |  | N/A
Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | September 30th, 2026 | Q3/2027 |  | Q3/2027
Prepare to adopt simplified recycle profiles | All Recycle profile changes [except DOs] can be configured in the current production environment. | Currently Available |  | Q3/2027
Messaging/Reporting
Settlement
Adopt new ISO 20022 message format | July 6, 2026 | November 13, 2026 |  | Q3/2027
Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | September 30, 2026 | November 13, 2026 |  | Q3/2027
Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) - Available through the SDX Portal (& through SFTP) | September 30th, 2026 | Q4/2026 |  | Q3/2027

## Quarter-Date Mapping (hidden)
Date | Quarter | Quarter | Last Date
January | Q1 | Q1 | 2026-03-31
February | Q1 | Q2 | 2026-06-30
March | Q1 | Q3 | 2026-09-30
April | Q2 | Q4 | 2026-12-31
May | Q2
June | Q2
July | Q3
August | Q3
September | Q3
October | Q4
November | Q4
December | Q4

## Checklist - old (hidden)
# | Task | Application | Available in PSE | Available in Production | Suggested Migration Date | Required Migration Date
CONNECTIVITY
1 | Clients who send and/or receive messages to/from DTCC will need to connect to new QMgrs on MQ Internet Passthrough (IPT) and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions. | Settlement | 2026-01-21 | Q2/2026 |  | Q3/2027
|  | 24x5 | Q4/2025 Required to participate in extended trading | 2026-06-28 |  | 2026-06-28
|  | UTC | Q4/2026 | Q2/2027 |  | Q4/2028
|  | CNS | Q1/2027 | Q2/2027 |  | Q3 2028
|  | ETF | Q2/2027 | Q4/2027 |  | Q3 2028
2 | Clients who send and/or receive files to/from DTCC will need to migrate off FTP, FTPS and NDM products to sFTP file transfers and provide new Security Certificate DN information and onboarding documentation, with new product subscriptions | Settlement | Q1/2026 | Q2/2026 |  | Q3/2027
|  | UTC | Q4/2026 | Q2/2027 |  | Q4/2028
|  | CNS | Q1/2027 | Q2/2027 |  | Q3 2028
|  | ETF | Q2/2027 | Q4/2027 |  | Q3 2028
3 | SDX Portal Application Entitlements | Onboard SACs | Mid-Feb 2026 | End-March 2026
|  | Report Viewer Role | Mid-Feb 2026 | End-March 2026 |  | Q3/2027
4 | Adopt new ISO message format | Settlement | Q2/2026 | Q4/2026 |  | Q3/2027
|  | 24x5 | N/A | N/A |  | N/A
|  | CNS | TBD | Q2/2027 |  | Q3 2028
|  | ETF | TBD | Q2/2027 |  | Q3 2028
| Adopt new FIX message format | UTC | TBD | TBD |  | TBD
| Adopt new ISO-aligned CSV report format (replaces machine-readable output (MRO)) | Settlement | Q2/2026 | Q4/2026 |  | Q3/2027
|  | CNS | TBD | Q2/2027 (production migration begins) |  | Q3 2028
|  | ETF | TBD | Q4/2027 ([roduction migration begins) |  | Q3 2028
| Adopt new CNS FIX-aligned CSV reports (replacement of MRO’s) | UTC | Q1/2026 | Q4/2028 |  | Q3/2027
| Clients who connect to UTC via FIX will need to connect via a new IP address. (24X5 only) | UTC | 2026-01-11 | 2026-06-28 |  | 2026-06-28
| Prepare for 24x5 trading including the requirement to support a new FIX Tag 715 “Clearing Business Date” field on report output | UTC | 2026-01-11 | 2026-06-28 |  | June 28,2026
| Prepare for 24x5 trading including the requirement to support a new FIX Tag 336 “9A/9B overnight processing” field on report output | UTC | 2026-02-12 | 2026-06-28 |  | June 28,2026
| Obtain interface usage reports from DTC and NSCC | ALL | N/A | N/A | Production reports are currently available should be requested completed by March 31, 2026 Q2/2026 | N/A
| Connect to DTCC’s new ISO 20022 test facility | Settlement | 2026-03-04 | N/A | Access granted by your Super Access Coordinator (SAC) | Optional
SETTLEMENT
| Obtain profile usage reports from DTC | Settlement | N/A | N/A | Production reports are currently available should be requested completed by March 31, 2026 Q2/2026 | N/A
| Prepare for the introduction of partial delivery authorization and auto-partial processing in DTC | Settlement | Q3/2026 | Q3/2027 |  | Q3/2027
| Adopt the ISO 20022 formats (replacement of proprietary formats & ISO 15022) | Settlement | Q2/2026 | Q4/2026 | Production migration to the new ISO20022 message formats can begin from Q4 2026 with a deadline of Q3 2027 | Q3/2027
| Adopt new ISO-aligned CSV reports (replacement of proprietary Formats) | CDTS 2.0 | Q2/2026 | Q4/2026 |  | Q3/2027
|  | SDX Portal | Q2/2026 | Q4/2026 |  | Q3/2027
| Accommodate the ability to submit DO and PO transactions with a “hold” indicator – this will be available Q3/2027 - Member usage will be optional | Settlement | Q3/2026 | Q3/2027 |  | Q3/2027
| Adopt simplified delivery authorization profiles | Settlement | Target state Delivery Authorization profile changes can be configured in the current production environment. Only the ability to establish discrete delivery profiles for same day settling CNS obligations is new functionality. | N/A | Migrate profiles by March 31, 2027 | Q3/2027
| Adopt simplified Receiver Authorized Delivery (RAD) profiles | Settlement | Target state RAD profile changes can be configured in the current production environment. Only the ability to subject Free DOs to RAD is new functionality | N/A | Migrate profiles by March 31, 2027 | Q3/2027
| New profile option - Prepare for the ability to subject same day settling CNS obligations to Deliverer Authorization | Settlement | Q3/2026 | Q3/2027 |  | Q3/2027
| New profile option - Prepare for the ability to subject free DOs to RAD approval | Settlement | Q3/2026 | Q3/2027 |  | Q3/2027
| Prepare to adopt simplified recycle profiles | Settlement | All Recycle profile changes can be configured in the current production environment. DOs cannot be established in the current production environment. | N/A | Migrate profiles by March 31, 2027 | Q3/2027
| Migration from NSCC CNS level 1 exemption processing to DTC Deliver Authorization process (Also refferenced in the Clearing section of this report.) |  | Currently Available | Currently Available |  | TBD
| Adopt for the mandatory reintroduction of failed (dropped) DO transactions | Settlement | The ability to reintroduce failed trades exists in the current production environment | N/A | Migrate profiles by March 31, 2027 | Q3/2027
CLEARING
| Prepare for the ability for introducing/executing broker dealers to receive UTC trade capture output of these transactions (MPID). | UTC | 2026-02-15 | 2026-06-30 |  | Optional Change
| Migration from NSCC CNS level 1 exemption processing to DTC Deliver Authorization process (Also refferenced in the Settlement section of this report.) |  | Currently Available | Currently Available |  | TBD
| Conduct CNS regression testing | CNS | 2026-07-13 | 2026-11-16 | Regression testing should be completed by September 30 | 2026-11-16
| Adopt / Test new online CSV reports (replacement of Print Image Format) | SDX Portal | Q2/2026 | Q4/2026 |  | Q4/2026
| New CNS Product ID available | CNS | Q2/2026 | TBD |  | TBD
| CNS ISO-aligned CSV report specifications available | CNS | Q2/2026 | TBD |  | Q3/2028
| Adopt new CNS product IDs | CNS | Q1/2027 | Q2/2027 |  | Q3/2028
| Adopt new CNS ISO-aligned CSV reports (replacement of MRO’s) | CNS | Q1 2027 | Q2/2027 | Migration to new ISO-aligned CSV reports starts in Q2 2027 with a deadline of Q3 2028 | TBD
| Conduct ETF regression testing | ETF | Q4 2026* | 2027-06-28 | Regression testing should be completed by May 28 | 2027-06-28
| Adopt/Test new online CSV reports (replacement of Print Image Format) | ETF | Q2 2027 | Q4 2027* |  | Q3 2028*
| New ETF Product ID available | ETF | Q1 2027 | Q1 2027 |  | Q3 2028*
| Adopt new ETF product IDs | ETF | Q2 2027 | Q4 2027* |  | Q3 2028*
DECOM
| Decom CNS Print Image Reports | CNS | N/A | N/A | Print image reports decom in PSE october 15 | 2026-11-16
|  | ETF | N/A | N/A |  | TBD
|  | Settlement | N/A | N/A | Decom in PSE on July 15 | 2027-08-01
WE NEED TO ADD IN THE ETF CHANGES TOO PLEASE
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. @Kaufman, Hannah - should we add a row for SDX entitlements - this is for when SDX (Securities Data Experience UI) will be made available for clients - to view /download reports (CNS CSV reports that replace the print image) - to view /download reports (Settlement CSV reports that are new reports - need to check what reports will be available in SDX) - there will also be ETF CSV reports that replace print image reports (3 CSV reports available for the Q2 2027 production go live - need to check when available in PSE)
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. @Kaufman, Hannah @Petrosyan, Levan - Is a DN security cert and product subscriptions relevant for MQ?
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. @Kaufman, Hannah - I though it was only the connection to the new FIX engine that was required? What do clients need to do for MQ?
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kaufman, Hannah @Abel, John F. - this should be production date which I believe is Q2 2027 but check the test approach document which Inga has as that has the details for CNS
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kaufman, Hannah @Abel, John F. - check for ETF when the connectivity is available for production migration think this is Q4 2027 timeframe (check with @Petrosyan, Levan )
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. @Kaufman, Hannah @Petrosyan, Levan - same question for SFTP
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kaufman, Hannah , please remove all gaps in the cells - I removed a few in the fist section but please look at the rest of the file
Note on F41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. - is this a profile change? Reply: It is. Today, members can elect to have their fails automatically reintroduced or not. In the future, fails will be automatically reintroduced. They have the ability to make this change in the current processing environment but must be prepared to support automatic reintroduction of fails beginning Q3.27.
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. - should we move this to the Settlement section as well? And reference it with CNS and Settlement as application Reply: Done.
Note on D45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. @Colacino, Louis - please confirm when Client testing opens up for CNS - this has moved I think to later in Q2 Reply: AD will be ready late June and have proposed July 13th for all reports to be available for client regression testing. I am ok with that date
Note on B60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. , @Kaufman, Hannah - is this related to CNS? - the production date is November 16, 2026, and please add CNS - in column C if it is CNS Reply: Yes, CNS. Do we need to add it for other applications?
Note on B72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Abel, John F. @Kaufman, Hannah @Bugaj, Jacek @Petrosyan, Levan - Please add in similar changes for ETF - Print image decomm (Q2 2027), CSV Reports available in SDX replacing 3 print image reports) (Q2 2027), ISO-aligned CSV reports placing MRO (PSE I think Q2 2027 and Prod Q4 2027)